## tblRAIDCATEGORY
_id | name | description
1 | Finance | Finance
2 | Human Resource | Human Resource

## tblRAIDSTATUS
_id | name | description
1 | Open | Open
2 | Close | Close

## tblRAIDREGISTER
_id | name | description
1 | RAID register or log | RAID register or log

## tblRAID
_id_raid | _id_logfame | _id_register | _id_raid_category | _id_originator | _id_owner | _id_frequency | name | description | date_raised
1 | 1 | 1 | 1 | 1 | 4 | 1 | Financial | Unable to deliver classes due to building services failure | 01/01/2020
2 | 1 | 1 | 1 | 1 | 2 | 2 | Service delivery | Failure to adhere to maintenance programme resulting in unreliable laboratory equipment | 01/01/2021
3 | 1 | 1 | 2 | 1 | 8 | 6 | H&S | Failure to comply with H&S practices – correct storage and handling when using chemicals | 01/01/2022
4 | 1 | 1 | 1 | 1 | 17 | 4 | Reputation | Loss of essential information due to IT failure | 01/01/2023
5 | 1 | 1 | 2 | 1 | 6 | 3 | Finance | The project delivery is delayed | 01/01/2024
6 | 1 | 1 | 2 | 1 | 12 | 5 | Service delivery | Unable to provide secure campus due to unavailability of security equipment on demand | 01/01/2025
7 | 1 | 1 | 2 | 1 | 2 | 2 | Service delivery | Electronic monitoring equipment unavailable on demand | 01/01/2026
8 | 1 | 1 | 2 | 1 | 13 | 1 | Service delivery | Reliance on contractors to provide essential services | 01/01/2027
9 | 1 | 1 | 2 | 1 | 16 | 3 | Legal & regulatory | Breach of building act | 01/01/2028
10 | 1 | 1 | 1 | 1 | 5 | 4 | Adverse media coverage | Poorly presented high profile event | 01/01/2029
11 | 1 | 1 | 1 | 1 | 6 | 5 | Product quality | Inaccurate information presented during a lecture or incorrect instructions given when using equipment | 01/01/2030
12 | 1 | 1 | 1 | 1 | 7 | 6 | Product quality | Poor student experience due to course material not available due to bad planning | 01/01/2031
13 | 1 | 1 | 1 | 1 | 8 | 2 | Reputation | Poor student experience due to inadequate information/administrative systems. Courses not properly marketed. | 01/01/2032
14 | 1 | 1 | 2 | 1 | 13 | 1 | Finance | Loss of funding from external agencies for research because of inability to produce high calibre Post Graduates. | 01/01/2033
15 | 1 | 1 | 1 | 1 | 1 | 4 | HR | Unable to deliver quality services due to our inability to attract and retain high calibre staff | 01/01/2034
16 | 1 | 1 | 1 | 1 | 3 | 4 | Assumption | Mentors will have enough protected time to be successful | 01/01/2035
17 | 1 | 1 | 1 | 1 | 4 | 4 | Assumption | Requires support of Chair and/or Director | 01/01/2036
18 | 1 | 1 | 2 | 1 | 6 | 4 | Assumption | Funding climate is supportive | 01/01/2037
19 | 1 | 1 | 1 | 1 | 7 | 3 | Issue | Staff serious injury andenvironmental damage | 01/01/2038
20 | 1 | 1 | 1 | 1 | 9 | 3 | Issue | Theft, unauthorised access. | 01/01/2039
21 | 1 | 1 | 1 | 1 | 10 | 3 | Issue | Media coverage resulting in poor reports in national press publications and national TV | 01/01/2040
22 | 1 | 1 | 2 | 1 | 11 | 2 | Dependency | New company logo to be issued by Corporate Affairs to be used by project. | 01/01/2041
23 | 1 | 1 | 1 | 1 | 12 | 2 | Dependency | Dependency | 01/01/2042
24 | 1 | 1 | 1 | 1 | 2 | 2 | Dependency | Dependency | 01/01/2043

## tblCOMPONENT_RAID
_id_raid | _id_activity | _id_component | _id_raid
1 | 1 | 1 | 1
1 | 2 | 2 | 2
1 | 3 | 3 | 3
|  | 4 | 4
|  | 5 | 5
|  | 6 | 6
|  | 7 | 7
|  | 8 | 8
|  | 9 | 9
|  | 10 | 10
|  | 11 | 11
|  | 12 | 12
|  | 13 | 13
|  | 14 | 14
|  | 15 | 15
|  | 16 | 16
|  | 17 | 17
|  | 18 | 18
|  | 19 | 19
|  | 20 | 20
|  | 21 | 21
|  | 22 | 22
|  | 23 | 23
|  | 24 | 24
|  | 25 | 1
|  | 26 | 2
|  | 27 | 3
|  | 28 | 4
|  | 29 | 5
|  | 30 | 6
|  | 31 | 7
|  | 32 | 8
|  | 33 | 9
|  | 34 | 10
|  | 35 | 11
|  | 36 | 12
|  | 37 | 13
|  | 38 | 14
|  | 39 | 15
|  | 40 | 16
|  | 41 | 17
|  | 42 | 18
|  | 43 | 19
|  | 44 | 20
|  | 45 | 21
|  | 46 | 22
|  | 47 | 23
|  | 48 | 24
|  | 49 | 1
|  | 50 | 2
|  | 51 | 3
|  | 52 | 4
|  | 53 | 5
|  | 54 | 6
|  | 55 | 7
|  | 56 | 8
|  | 57 | 9
|  | 58 | 10
|  | 59 | 11
|  | 60 | 12
|  | 61 | 13
|  | 62 | 14
|  | 63 | 15
|  | 64 | 16
|  | 65 | 17
|  | 66 | 18
|  | 67 | 19
|  | 68 | 20
|  | 69 | 21
|  | 70 | 22
|  | 71 | 23
|  | 72 | 24
|  | 73 | 1
|  | 74 | 2
|  | 17 | 3
|  | 18 | 4
|  | 19 | 5
|  | 20 | 6
|  | 21 | 7
|  | 22 | 8
|  | 23 | 9
|  | 24 | 10
|  | 25 | 11
|  | 26 | 12
|  | 27 | 13
|  | 28 | 14
|  | 29 | 15
|  | 30 | 16
|  | 31 | 17
|  | 32 | 18
|  | 33 | 19
|  | 34 | 20
|  | 35 | 21
|  | 36 | 22
|  | 37 | 23
|  | 38 | 24

## tblASSUMPTION
_id_raid
16
17
18

## tblRISKCONSEQUENCE
_id | _id_risk | name | description
1 | 1 | Finance | Up to $100,000 in repairs to services and other losses
2 | 2 | Service delivery | Cancellation of experiments
3 | 2 | Service delivery | Classes impacting tutorial programme and delayed research projects
4 | 3 | H&S | Staff serious injury andenvironmental damage
5 | 3 | H&S | Lost of time
6 | 3 | H&S | Prosecution by DoL
7 | 4 | Reputation | Unable to access data or provide reports/information to external gulators/stakeholders.
8 | 4 | Reputation | Unable to monitor performance
9 | 5 | Service delivery | Project overrun resulting in excess of $150,000 in additional rent or hire payments
10 | 6 | Service delivery | University premises not secured due to inoperative electronic security equipment.
11 | 6 | Service delivery | Theft, unauthorised access.
12 | 7 | Service delivery | Unable to monitor premises resulting in potential for loss/theft/vandalism
13 | 8 | Service delivery | Lower level of institutional knowledge resulting in inflexible models of service delivery.
14 | 8 | Service delivery | Loss of institutional/corporate knowledge
15 | 9 | Legal & regulatory | Delay to project and prosecution
16 | 10 | Adverse media coverage | Media coverage resulting in poor reports in national press publications and national TV
17 | 11 | Product quality | Poor performance when graduate leaves VUW and is employed in industry. Also poor reputation
18 | 12 | Product quality | Student unable to continue with course because of poor performance
19 | 13 | Reputation | Students unable to access courses
20 | 14 | Finance | Unable to run Post Graduate programmes. Also impacting upon VUW reputation.
21 | 14 | Finance | Unable to service premises in which to deliver programmes.
22 | 15 | HR | Unable to deliver and support high quality teaching programmes

## tblRISKROOTCAUSE
_id | _id_risk | name | description
1 | 1 | Inadequate monitoringof assets by end users | Inadequate monitoring of assets by end users
2 | 1 | Ineffective management of norms and standards allocation (Repairs and renovation) | Ineffective management of norms and standards allocation (Repairs and renovation)
3 | 2 | Decentralisation of Asset Management in terms of the reporting functions (creation of Valid, accurate and complete FAR) | Decentralisation of Asset Management in terms of the reporting functions (creation of Valid, accurate and complete FAR)
4 | 2 | Unhealthy life style | Unhealthy life style
5 | 3 | In adequate human resource capacity (within asset mgt sections) to manage the FAR | In adequate human resource capacity (within asset mgt sections) to manage the FAR
6 | 4 | Lack of Appropriately skilled personnel. | Lack of Appropriately skilled personnel.
7 | 5 | Inadequate management of documents | Inadequate management of documents
8 | 6 | Inadequate reporting of lost assets | Inadequate reporting of lost assets
9 | 7 | Fraud and corruption | Fraud and corruption
10 | 8 | Escalating personnel cost | Escalating personnel cost
11 | 9 | Inadequate budget monitoring. | Inadequate budget monitoring.
12 | 10 | Inadequate budget | Inadequate budget
13 | 10 | Lack of proper induction programme and manual for new staff. | Lack of proper induction programme and manual for new staff.
14 | 11 | Limited financial management skills | Limited financial management skills
15 | 12 | Non compliance with budgetary policies and procedures. | Non compliance with budgetary policies and procedures.
16 | 13 | Unfunded mandates | Unfunded mandates
17 | 14 | Lack of integrated approach | Lack of integrated approach
18 | 15 | Unavailability of systems (SCM processes, recruitment processes) | Unavailability of systems (SCM processes, recruitment processes)
19 | 16 | Fraudulent qualifications | Fraudulent qualifications
20 | 17 | Budgetary constrains | Budgetary constrains

## tblRISK
_id_raid
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## tblISSUE
_id_raid
19
20
21

## tblDEPENDENCY
_id_raid | how_validated | validated
22 | through docs | 1
23 | through docs | 0
24 | through docs | 1

## tblRAIDLIKELIHOOD
_id | name | description | value
1 | Very low | Extremely unlikely Less than 5% chance of occurring | 1
2 | Low Unlikely | 5% - 25% chance of occurring | 2
3 | Medium Possible | 25%-60% chance of occurring | 3
4 | High Likely | 60% - 80% chance of occurring | 4
5 | Very high | Almost certain. 80%-100% chance of occurring | 5

## tblRAIDIMPACT
_id | name | description | value
1 | Insignificant | Consequences are very low, minor disruption. | 1
2 | Minor | Losses may disrupt services for a short period. Financial losses may be in the region of $10,000 Disruption to a single area of the business. | 2
3 | Moderate | u6yuyysgmjfhyjtjtthjyhyjuytgjyhtzSssA | 3
4 | Serious | Service lost for period exceeding 1 week. Financial loss $100,000 – $1M. Adverse media coverage for 1 week. Internal investigation or by an external source/regulator. Staff contractor or visitor suffers serious injury. Impact to multiple and diverse areas of the business. Significant senior management intervention required including external assistance. | 4
5 | Very serious | Significant resources required to recover from impact. Legal consequences resulting in prosecution. Financial loss >$10M. Staff, contractor or visitor involved in a fatal event. Adverse media coverage for an extended period. Complete loss of service delivery affecting all VUW critical functions. Immediate SMT and Council intervention required | 5

## tblPIMSET
_id_raid_likelihood | _id_raid_impact | _id_robot | score
1 | 1 | 1 | 1
1 | 2 | 1 | 2
1 | 3 | 1 | 3
1 | 4 | 1 | 4
1 | 5 | 2 | 5
2 | 1 | 1 | 2
2 | 2 | 1 | 4
2 | 3 | 2 | 6
2 | 4 | 2 | 8
2 | 5 | 2 | 10
3 | 1 | 1 | 3
3 | 2 | 2 | 6
3 | 3 | 2 | 9
3 | 4 | 3 | 12
3 | 5 | 3 | 15
4 | 1 | 1 | 4
4 | 2 | 2 | 8
4 | 3 | 3 | 12
4 | 4 | 3 | 16
4 | 5 | 3 | 20
5 | 1 | 2 | 5
5 | 2 | 2 | 10
5 | 3 | 3 | 15
5 | 4 | 3 | 20
5 | 5 | 3 | 25

## tblRAIDASSESSMENT
_id | _id_status | _id_raid_likelihood | _id_raid_impact | score
1 | 1 | 3 | 4 | 12
2 | 1 | 3 | 5 | 15
3 | 1 | 4 | 4 | 16
4 | 1 | 3 | 3 | 9
5 | 1 | 3 | 4 | 12
6 | 1 | 3 | 5 | 15
7 | 1 | 4 | 4 | 16
8 | 1 | 3 | 3 | 9
9 | 1 | 4 | 5 | 20
10 | 1 | 3 | 4 | 12
11 | 1 | 4 | 5 | 20
12 | 1 | 3 | 4 | 12
13 | 1 | 4 | 5 | 20
14 | 1 | 3 | 3 | 9
15 | 1 | 4 | 4 | 16
16 | 1 | 3 | 4 | 12
17 | 1 | 3 | 5 | 15
18 | 1 | 4 | 3 | 12
19 | 1 | 4 | 5 | 20
20 | 1 | 3 | 2 | 6
21 | 1 | 5 | 4 | 20
22 | 1 | 1 | 4 | 4
23 | 1 | 4 | 1 | 4
24 | 1 | 2 | 3 | 6

## tblMITIGATIONSTRATEGY
_id | name | description
1 | Avoid | The project team can avoid the risk by changing the activity that will create the risk
2 | Mitigate | These are activities designed to reduce the impact to the project if the risk were to occur.
3 | Transfer | This activity includes the process to transfer or share the risk with a third party who may have more expertise
4 | Accept | Due to its low probability and Impact, the best action is to accept the risk.

## tblMITIGATIONACTION
_id | _id_raid_assessment | _id_mitigation_strategy
1 | 1 | 1
2 | 2 | 2
3 | 3 | 3
4 | 4 | 4
5 | 5 | 1
6 | 6 | 2
7 | 7 | 3
8 | 8 | 4
9 | 9 | 1
10 | 10 | 2
11 | 11 | 3
12 | 12 | 4
13 | 13 | 1
14 | 14 | 2
15 | 15 | 3
16 | 16 | 4
17 | 17 | 1
18 | 18 | 2
19 | 19 | 3
20 | 20 | 4
21 | 21 | 1
22 | 22 | 2
23 | 23 | 3
24 | 24 | 4

## tblPIM (hidden)
_id | name | description
1 | mentor matrix | mentor matrix

## tblRISKREGISTER (hidden)
_id_register
1

## tblASSUMPTIONREGISTER (hidden)
_id_register
2

## tblISSUEREGISTER (hidden)
_id_register
3

## tblDEPENDENCYREGISTER (hidden)
_id_register
4

## tblRAIDLOG (hidden)
_id | _id_logframe | _risk_register | _id_ass_register | _id_issue_register | _id_dep_register | name | description
1 | 1 | 1 | 2 | 3 | 4 | log 1 | Raid Log 1

## tblRISKCRITERIA (hidden)
_id | name | description | lower_limit | upper_limit
1 | Very low | Manage within existing controls. Monitor annually ACCEPT THE RISK (Contingency Plan) | 1 | 15
2 | Low | Manage within existing controls. Monitor 6 monthly ACCEPT THE RISK (Contingency Plan) | 16 | 20
3 | Medium | Evaluate efficiency of existing controls. Develop and implement additional control mechanisms. Monitor quarterly TRANSFER THE RISK (Preventive Plan) | 21 | 25
4 | High | Implement mitigation plan Escalate/report to senior management Monitor monthly MITIGATE THE RISK (Preventive Plan) | 26 | 30
5 | Very high | Implement mitigation immediately Escalate to senior management Monitor weekly AVOID THE RISK | 31 | 100

## tblRISKIMPACTSET (hidden)
_id_register | _id_risk_impact
1 | 1
1 | 2
1 | 3
1 | 4
1 | 5

## tblRISKCRITERIASET (hidden)
_id_register | _id_risk_criteria
1 | 1
1 | 2
1 | 3
1 | 4
1 | 5

## tblREVIEWCOMMENT (hidden)
_id | _id_staff | _id_milestone_review

## tblRISKREVIEW (hidden)
_id_review | _id_risk | residual_risk

## tblASSUMPTIONREVIEW (hidden)
_id_review | _id_assumption | assumption_rating

## tblISSUEREVIEW (hidden)
_id_review | _id_issue | priority

## tblDEPENDENCYREVIEW (hidden)
_id_review | _id_dependency | dependency_rating

## tblRISKANALYSIS (hidden)
_id | _id_risk_milestone | _id_likelihood | _id_riskimpact
1 | 1 | 2 | 3
2 | 1 | 2 | 4
3 | 1 | 2 | 4
4 | 1 | 2 | 3
5 | 1 | 3 | 4
6 | 1 | 3 | 4
7 | 1 | 2 | 3
8 | 1 | 2 | 5
9 | 1 | 2 | 3
10 | 1 | 2 | 4
11 | 1 | 2 | 5
12 | 1 | 2 | 4
13 | 1 | 2 | 5
14 | 1 | 2 | 5
15 | 1 | 2 | 4
16 | 2 | 2 | 3
17 | 2 | 2 | 4
18 | 2 | 2 | 4
19 | 2 | 2 | 3
20 | 2 | 3 | 4
21 | 2 | 3 | 4
22 | 2 | 2 | 3
23 | 2 | 2 | 5
24 | 2 | 2 | 3
25 | 2 | 2 | 4
26 | 2 | 2 | 5
27 | 2 | 2 | 4
28 | 2 | 2 | 5
29 | 2 | 2 | 5
30 | 2 | 2 | 4
31 | 1 | 2 | 3

## tblACTION (hidden)
_id_workplan
10
11
12

## tblACTIONTASK (hidden)
_id_task | _id_action

## tblMILESTONE_ACTION (hidden)
_id_review | _id_action_task

## tblCURRENTCONTROL (hidden)
_id_risk_action

## tblADDITIONALCONTROL (hidden)
_id_risk_action

## tblASSUMPTIONACTION (hidden)
_id_action | _id_ass_review

## tblISSUEACTION (hidden)
_id_action | _id_issue_review

## tblDEPENDENCYACTION (hidden)
_id_action | _id_dep_review

## tblACTIONASSIGNMENT
_id | _id_mitigation_action | _id_staff
1 | 1 | 1
2 | 2 | 1
3 | 3 | 1
4 | 4 | 1
5 | 5 | 1
6 | 6 | 1
7 | 7 | 1
8 | 8 | 1
9 | 9 | 1
10 | 10 | 1
11 | 11 | 1
12 | 12 | 1
13 | 13 | 1
14 | 14 | 1
15 | 15 | 1
16 | 16 | 1
17 | 17 | 1
18 | 18 | 1
19 | 19 | 1
20 | 20 | 1
21 | 21 | 1
22 | 22 | 1
23 | 23 | 1
24 | 24 | 1

## tblRISK1 (hidden)
_id_risk_issue
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## tblPRECEDINGACTION
_id | _id_mitigation_action | _id_preceding_action
1 | 1 | 2
2 | 2 | 3

## tblPREVENTATIVEPLAN1 (hidden)
_id_mitigation_plan
11

## tblISSUEPLAN (hidden)
_id_mitigation_plan
12

## tblRISKEVALUATION (hidden)
_id_risk_analysis | _id_mitigation_action
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6 | 6
7 | 7
8 | 8
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
15 | 15
16 | 16
17 | 17
18 | 18
19 | 19
20 | 20
21 | 21
22 | 22
23 | 23
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
1 | 31
2 | 32
3 | 33
4 | 34
5 | 35
6 | 36
7 | 37
8 | 38
9 | 39
10 | 40
11 | 41
12 | 42
13 | 43
14 | 44
15 | 45
16 | 46
17 | 47
18 | 48
19 | 49
20 | 50
21 | 51
22 | 52
23 | 53
24 | 54
25 | 55
26 | 56
27 | 57
28 | 58
29 | 59
30 | 60
1 | 61
2 | 62
3 | 63
4 | 64